## Sheet1
Task ID | Task Description | Depencencies
1 | Tune motor PID | 11
2 | Create robot rotation matrices | 11
3 | Get robot to interact with ROS | 11; 17; 18
4 | Develop path planning algorithm | -
5 | Get robot to move to specific point | 11, 4, 1, 2, 19; 3
6 | Get robot to intercept ball | 20, 19, 5; 3
7 | Get robot to score with ball | 5; 6
8 | Get robot to kick ball | 12; 6; 13
9 | Design robot body | -
10 | Print robot body | 9
11 | Assemble prototype robot | 10
12 | Build kicker | 13
13 | Design kicker | -
14 | Design jacket | -
15 | Mount jacket | 14; 11
16 | Get robot to spin | 1; 11; 3
17 | Install software on Raspberry Pi | -
18 | Install software on PSoC | -
19 | See robot on field | 15
20 | See ball on field | -
21 | Get robot to pass ball | 8; 6
22 | Develop offensive and defensive plays | -
23 | Simulator Competition | 22
24 | Skills Tournament | 16; 5
25 | Play Tournament | 7; 6
26 | Practice Competitions | 22; 24; 25; 8; 21
27 | Final Competition | 26
28 | Design final robot | 11; 24
29 | Build final robot | 28
30 | Implement Estimator | -
31 | Implement dribbling | -
32 | Implement get ball in open skill | -
33 | Figure out role coordination | -
34 | Deal with Vision lag | 19, 20